

Hello Dominic,

After going through your website requirements, below is a listed view of workable time frame and the cost:

**Time Schedule:**

1. System analysis and laying out the framework: 1 week – >1st – 5th June
2. Database design (for storing the news and announcements articles, images, and other necessary resources): 1 week -> 7th – 12th June
3. Backend development (for communication with the database, and creating the skeleton for the whole website): 5 days –> 13th June – 18th June
4. Working on the front end (interface) i.e. the part visible to the user:
5. Home Page: 10 days -> 18th June – 28th June
6. Designing the 3 group pages i.e. MYM, YFC, and YACA 1 week –> 30th June – 9th July
7. The remaining 6 pages i.e. organogram, resources, news and announcements, leadership corner and contacts: 1 week –> 10th July – 17th July
8. Testing for any bugs and inspection by the project manager (you) and owners (Catholic Youth): 1 week –>19th July – 25th July
9. Getting a good host, uploading the web content and getting it online and running: 3 days –> 26th – 28th July

Even though not mentioned, from stage 4 (a) on 28th June, you can start inspecting the website to see if it goes according to listed requirements. This is the first physical deliverable.